## Dashboard
AFME PROJECT ENGINEERING & DELIVERY ¦ PED-01
FOOD MANUFACTURING ENGINEERING PROJECT MANAGEMENT TOOLKIT
Project Health KPI | Value | Project Control Principle
Overall completion | 0% | A food-manufacturing engineering project is not complete when the equipment runs. Completion requires controlled scope, safe installation, technical and food-safety acceptance where relevant, commissioning evidence, documentation, PM/calibration setup, spares, training, handover and confirmation that the promised business benefit is actually delivered.
Open critical risks | 0
Overdue actions | 0
Budget approved | 0
Forecast final cost | 0
Forecast variance | 0
Open changes | 0 | Health Area | RAG / Status
Open snags | 0 | Scope | Use Stage Gates / Change Control
Handover completion | 0% | Programme | Use Programme & Actions
Current stage |  | Risk / H&S / Food Safety | Use RAID + Design Review

## Project Charter
PROJECT CHARTER / BRIEF
Field | Entry | Guidance | Approval / Owner
Project title |  | Clear project name
Project ID |  | Site/project reference
Sponsor |  | Accountable business sponsor
Project lead |  | Day-to-day delivery owner
Problem statement |  | What problem/opportunity exists?
Objective |  | Measurable outcome, not proposed solution
Success criteria |  | Capacity, safety, food safety, cost, reliability, quality, energy etc.
Scope included |  | Equipment, civils, services, controls, training etc.
Scope excluded |  | Explicit exclusions to prevent ambiguity
Current stage | Concept | Concept / Feasibility / Approval / Design / Procurement / Installation / Commissioning / Handover / Benefits
Target completion |  | Required operational/handover date
Approved budget |  | Approved CAPEX envelope
Production constraints |  | Shutdowns, launches, peak periods, access
Food-safety / Technical interfaces |  | HACCP, zoning, hygienic design, CCPs, allergens, inspection systems
H&S / statutory / CDM considerations |  | Dutyholders, permits, statutory inspection, construction activity
Utilities / infrastructure |  | Electrical, steam, gas, water, refrigeration, air, drainage, network
Key assumptions |  | Assumptions requiring validation
Key dependencies |  | Items outside direct project control
Primary stakeholders |  | Operations, Technical, Hygiene, H&S, Finance, Procurement etc.
Approval to proceed |  | Name/date/gate

## Stage Gates
Gate | Minimum Requirement / Question | Status | Evidence / Reference | Owner | Due Date | Approval / Decision | Comments
Gate 1 - Concept | Problem and objective defined | Not Started
Gate 1 - Concept | Sponsor and project lead identified | Not Started
Gate 1 - Concept | Initial scope/exclusions recorded | Not Started
Gate 1 - Concept | Initial food-safety/H&S/production impacts screened | Not Started
Gate 1 - Concept | Order-of-magnitude cost and timeline understood | Not Started
Gate 2 - Feasibility | Options appraised | Not Started
Gate 2 - Feasibility | Utilities/infrastructure capacity checked | Not Started
Gate 2 - Feasibility | Technical/Quality and H&S input obtained where relevant | Not Started
Gate 2 - Feasibility | Key risks/assumptions/dependencies logged | Not Started
Gate 2 - Feasibility | Indicative supplier/market solution validated | Not Started
Gate 2 - Feasibility | Business case and benefits defined | Not Started
Gate 3 - Approval | CAPEX/business approval secured | Not Started
Gate 3 - Approval | Budget and contingency confirmed | Not Started
Gate 3 - Approval | Governance and reporting agreed | Not Started
Gate 3 - Approval | CDM/client duties reviewed where applicable | Not Started
Gate 3 - Approval | Project programme and procurement route approved | Not Started
Gate 4 - Design Freeze | URS approved | Not Started
Gate 4 - Design Freeze | Design review complete | Not Started
Gate 4 - Design Freeze | Hygienic design/food-safety review complete where relevant | Not Started
Gate 4 - Design Freeze | Safety/guarding/isolation concept approved | Not Started
Gate 4 - Design Freeze | Utilities, controls and interfaces confirmed | Not Started
Gate 4 - Design Freeze | Maintainability/RAMS and spares reviewed | Not Started
Gate 4 - Design Freeze | Design changes formally controlled | Not Started
Gate 5 - Procurement | Technical/commercial comparison complete | Not Started
Gate 5 - Procurement | Supplier deviations closed or accepted | Not Started
Gate 5 - Procurement | FAT/SAT/acceptance criteria agreed | Not Started
Gate 5 - Procurement | Documentation/training/spares requirements included in PO/contract | Not Started
Gate 5 - Procurement | Delivery and installation dates confirmed | Not Started
Gate 6 - Installation Readiness | Production/shutdown release confirmed | Not Started
Gate 6 - Installation Readiness | Contractor/CDM arrangements complete | Not Started
Gate 6 - Installation Readiness | RAMS/method statements/permits/isolation/lifting reviewed | Not Started
Gate 6 - Installation Readiness | Hygiene segregation and contamination controls ready | Not Started
Gate 6 - Installation Readiness | Services/civils/access/storage/welfare ready | Not Started
Gate 6 - Installation Readiness | Commissioning resources and materials available | Not Started
Gate 7 - Commissioning | FAT actions closed/accepted | Not Started
Gate 7 - Commissioning | Installation inspected and safe | Not Started
Gate 7 - Commissioning | SAT complete | Not Started
Gate 7 - Commissioning | Calibration/inspection systems verified | Not Started
Gate 7 - Commissioning | Dry/wet/product commissioning complete as relevant | Not Started
Gate 7 - Commissioning | Performance acceptance criteria achieved | Not Started
Gate 7 - Commissioning | Technical/Quality validation/release complete where relevant | Not Started
Gate 8 - Handover | As-built drawings/manuals/certificates received | Not Started
Gate 8 - Handover | Software backups/access credentials controlled | Not Started
Gate 8 - Handover | PM/lubrication/calibration/asset register/CMMS live | Not Started
Gate 8 - Handover | Critical spares and warranty contacts in place | Not Started
Gate 8 - Handover | Operations/Engineering/Hygiene training complete | Not Started
Gate 8 - Handover | Snags risk-assessed and owned | Not Started
Gate 8 - Handover | Formal handover accepted | Not Started
Gate 9 - Benefits & Close | 30/60/90-day review completed | Not Started
Gate 9 - Benefits & Close | Benefits compared with business case | Not Started
Gate 9 - Benefits & Close | Reliability/performance issues reviewed | Not Started
Gate 9 - Benefits & Close | Open snags/actions closed or formally transferred | Not Started
Gate 9 - Benefits & Close | Final cost confirmed | Not Started
Gate 9 - Benefits & Close | Lessons learned recorded | Not Started
Gate 9 - Benefits & Close | Project formally closed | Not Started

## Programme & Actions
ID | Workstream | Task / Milestone | Dependency | Owner | Start Date | Due Date | Priority | Actual / Forecast Finish | Status | % Complete | Notes

## RAID Log
ID | Type | Description | Cause / Context | Impact | Likelihood (1-5) | Severity (1-5) | Priority | Mitigation / Response | Owner | Due Date | Escalation / Decision | Residual Priority | Status | Evidence / Notes
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review
Review

## Cost Tracker
PROJECT COST SUMMARY
Approved budget | 0
Approved contingency | 0
Committed / POs | 0
Actual invoiced | 0
Forecast final cost | 0
Forecast variance | 0
Cost ID | Category | Supplier | Description | PO / Ref | Committed | Actual | Forecast Final | Approved Change Ref | Owner | Notes

## Supplier Comparison
Requirement / Criterion | Weight % | Supplier A Score 1-5 | Supplier A Weighted | Supplier B Score 1-5 | Supplier B Weighted | Supplier C Score 1-5 | Supplier C Weighted | Evidence / Notes
Technical compliance with URS | 15
Food-industry / hygienic design capability | 10
Safety / guarding / compliance | 10
RAMS / maintainability | 8
Controls / automation compatibility | 8
Utilities / energy performance | 6
FAT / testing capability | 6
Documentation quality | 5
Training provision | 4
Critical spares / lead time | 5
Service / warranty support | 5
Obsolescence / lifecycle support | 4
Programme / delivery confidence | 6
Commercial / whole-life value | 8
TOTAL WEIGHT | 100 | SUPPLIER A | 0 | SUPPLIER B | 0 | SUPPLIER C | 0
Decision / rationale

## Design Review
ID | Design Review Topic | Requirement / Challenge | Status | Evidence / Drawing Ref | Action | Owner | Due Date | Approval / Comments
DR-001 | Process / performance | Capacity, rate, product range and performance criteria match approved URS. | Not Reviewed
DR-002 | Hygienic design | Product-contact materials, cleanability, drainability, hollow sections/dead spaces and contamination traps reviewed. | Not Reviewed
DR-003 | Food safety | CCP/preventive control, allergen, foreign-body, temperature and inspection-system interfaces reviewed. | Not Reviewed
DR-004 | Zoning | High-care/high-risk/low-risk segregation, airflow, personnel/material routes and equipment acceptance considered. | Not Reviewed
DR-005 | Cleaning & hygiene | Cleaning method, chemical compatibility, access, strip-down, water management and verification considered. | Not Reviewed
DR-006 | Personnel safety | Guarding, access, working at height, hot surfaces, stored energy and foreseeable intervention reviewed. | Not Reviewed
DR-007 | Isolation / LOTO | Safe electrical, pneumatic, hydraulic, steam, gas, refrigeration and mechanical isolation points defined. | Not Reviewed
DR-008 | Maintainability | Access to service items, component removal, lifting, diagnostics, service clearances and maintenance time reviewed. | Not Reviewed
DR-009 | Electrical | Site electrical standards, protection, panels, ingress rating, cables, earthing and spare capacity reviewed. | Not Reviewed
DR-010 | Controls / software | PLC/HMI/SCADA architecture, recipes, alarms, backups, network, cybersecurity/access and standards reviewed. | Not Reviewed
DR-011 | Utilities | Capacity/quality of electrical, steam, gas, water, compressed air, refrigeration and drainage confirmed. | Not Reviewed
DR-012 | Calibration | Measuring/monitoring devices, ranges, accuracy, access and calibration method defined. | Not Reviewed
DR-013 | Spares / standardisation | Preferred components, critical spares, lead times and obsolescence reviewed. | Not Reviewed
DR-014 | Environment / sustainability | Energy, water, effluent, refrigerants, waste, noise and environmental impacts considered. | Not Reviewed
DR-015 | Building / civils | Loads, foundations, drainage, penetrations, fire stopping, walls/ceilings/floors and access reviewed. | Not Reviewed
DR-016 | Documentation | Drawings, manuals, certificates, parts lists, software and training deliverables specified. | Not Reviewed
DR-017 | FAT/SAT | Test scripts and measurable acceptance criteria agreed before manufacture/installation. | Not Reviewed
DR-018 | Future change | Format changes, expansion, access and lifecycle support considered. | Not Reviewed

## Installation Readiness
ID | Readiness Check | Status | Evidence / Reference | Owner | Due Date | Escalation / Comments
IR-001 | Production shutdown/release formally confirmed | Not Ready
IR-002 | Scope/design frozen or open changes explicitly controlled | Not Ready
IR-003 | CDM applicability and dutyholder arrangements confirmed where relevant | Not Ready
IR-004 | Contractor competence/induction and site rules complete | Not Ready
IR-005 | RAMS/method statements reviewed and accepted | Not Ready
IR-006 | Permits and isolation plan prepared | Not Ready
IR-007 | LOTO points identified and tested where possible | Not Ready
IR-008 | Lifting/access equipment and plans available | Not Ready
IR-009 | Hygiene segregation/zip walls/barriers/foreign-body controls ready | Not Ready
IR-010 | Drain protection and water-control plan ready | Not Ready
IR-011 | Temporary power/services/fire arrangements controlled | Not Ready
IR-012 | Civils/foundations/penetrations/services complete | Not Ready
IR-013 | Delivery route, storage and laydown area available | Not Ready
IR-014 | Waste/skips/removal routes agreed | Not Ready
IR-015 | Welfare facilities available | Not Ready
IR-016 | OEM/controls/commissioning resources booked | Not Ready
IR-017 | FAT actions closed or accepted | Not Ready
IR-018 | Commissioning materials/product/test pieces available | Not Ready
IR-019 | Technical/Hygiene/Operations attendance agreed | Not Ready
IR-020 | Emergency/recovery plan for overrun or failed commissioning defined | Not Ready

## FAT SAT Commissioning
Test ID | Phase | System / Function | Test / Acceptance Requirement | Expected Result / Criteria | Actual Result / Evidence | Status | Defect / Action Ref | Witness / Owner | Date | Comments
T-001 | FAT | Mechanical build | Build matches approved drawings/URS | Conformance demonstrated |  | Not Tested
T-002 | FAT | Controls | I/O, recipes, alarms, interlocks and sequences tested | Approved test script passed |  | Not Tested
T-003 | FAT | Safety | Guards, safety circuits and emergency functions tested | Safe state demonstrated; actions recorded |  | Not Tested
T-004 | FAT | Documentation | Draft manuals, drawings, parts lists and certificates reviewed | Required documents available |  | Not Tested
T-005 | SAT | Installation | Equipment installed to approved design and site standards | Inspection accepted |  | Not Tested
T-006 | SAT | Utilities | Electrical/air/water/steam/refrigeration/drainage interfaces proven | Stable supply and no unacceptable leakage/defect |  | Not Tested
T-007 | SAT | Controls integration | Site PLC/SCADA/network/data interfaces proven | Communication and control correct |  | Not Tested
T-008 | Commissioning | Dry commissioning | No-product functional tests complete | Safe stable operation |  | Not Tested
T-009 | Commissioning | Wet/process commissioning | Process fluids/product simulation as applicable | No unacceptable leaks, control instability or hygiene issue |  | Not Tested
T-010 | Commissioning | Calibration | Critical instruments and inspection systems verified | Within defined tolerance |  | Not Tested
T-011 | Commissioning | Product trial | Product/process trial meets quality and food-safety criteria | Technical acceptance where required |  | Not Tested
T-012 | Commissioning | Performance | Rate/capacity/reliability acceptance run completed | Contract/URS performance criteria achieved |  | Not Tested
T-013 | Commissioning | Hygiene | Post-install clean and hygiene validation/inspection complete | Released for intended production use |  | Not Tested
T-014 | Handover | Training | Operators/engineers/hygiene trained | Competence/attendance evidence available |  | Not Tested

## Change Control
Change ID | Date Raised | Requested By | Description / Reason | Technical Impact | Food Safety / Quality Impact | H&S / Compliance Impact | Cost Impact | Programme Impact | Approval / Decision | Status | Implementation Evidence

## Snag List
Snag ID | Area / System | Description | Priority | Food Safety / H&S Impact | Owner | Target Date | Temporary Control | Closure Evidence | Status

## Handover
ID | Handover Requirement | Required? | Evidence / Location | Owner | Due Date | Status | Acceptance / Comments
HO-001 | As-built mechanical drawings | Yes |  |  |  | Not Started
HO-002 | As-built electrical drawings | Yes |  |  |  | Not Started
HO-003 | P&IDs / utility schematics where relevant | Yes |  |  |  | Not Started
HO-004 | OEM operating and maintenance manuals | Yes |  |  |  | Not Started
HO-005 | Parts lists / BOM | Yes |  |  |  | Not Started
HO-006 | Declarations/certificates/statutory documentation as applicable | Yes |  |  |  | Not Started
HO-007 | PLC/HMI/SCADA/software backups | Yes |  |  |  | Not Started
HO-008 | Passwords/access credentials controlled | Yes |  |  |  | Not Started
HO-009 | Network/IP/device records | Yes |  |  |  | Not Started
HO-010 | Asset IDs and asset register created | Yes |  |  |  | Not Started
HO-011 | CMMS hierarchy and PM tasks live | Yes |  |  |  | Not Started
HO-012 | Lubrication schedule created | Yes |  |  |  | Not Started
HO-013 | Calibration register/tasks live | Yes |  |  |  | Not Started
HO-014 | Critical spares identified and stocked/ordered | Yes |  |  |  | Not Started
HO-015 | Special tools/lifting equipment provided | Yes |  |  |  | Not Started
HO-016 | Operator training complete | Yes |  |  |  | Not Started
HO-017 | Engineering maintenance training complete | Yes |  |  |  | Not Started
HO-018 | Hygiene/cleaning training and method updated | Yes |  |  |  | Not Started
HO-019 | Risk assessments/SOPs/work instructions updated | Yes |  |  |  | Not Started
HO-020 | Technical/HACCP/change-control review complete where relevant | Yes |  |  |  | Not Started
HO-021 | Hygiene validation/release complete where relevant | Yes |  |  |  | Not Started
HO-022 | Warranty/service contacts recorded | Yes |  |  |  | Not Started
HO-023 | Open snags transferred with controls | Yes |  |  |  | Not Started
HO-024 | Final cost / PO closure complete | Yes |  |  |  | Not Started
HO-025 | 30/60/90-day review scheduled | Yes |  |  |  | Not Started

## Benefits Review
Benefit ID | Benefit Category | Business Case Baseline | Target | Actual 30 Day | Actual 60 Day | Actual 90 Day | Unit | Owner | Status | Evidence / Commentary
BEN-001 | Capacity / throughput | [7 empty] | Not Reviewed
BEN-002 | Labour | [7 empty] | Not Reviewed
BEN-003 | Waste / yield | [7 empty] | Not Reviewed
BEN-004 | Energy | [7 empty] | Not Reviewed
BEN-005 | Water | [7 empty] | Not Reviewed
BEN-006 | Reliability / downtime | [7 empty] | Not Reviewed
BEN-007 | Safety | [7 empty] | Not Reviewed
BEN-008 | Food safety / compliance | [7 empty] | Not Reviewed
BEN-009 | Quality | [7 empty] | Not Reviewed
BEN-010 | Maintenance cost | [7 empty] | Not Reviewed
BEN-011 | Other financial benefit | [7 empty] | Not Reviewed

## Meeting Decisions
Record ID | Date | Meeting / Topic | Decision / Action | Reason / Context | Owner | Due Date | Status | Reference / Evidence

## How to Use
AFME PED-01 Engineering Project Management Toolkit | Version 1.0 ¦ September 2026
1 | Complete Project Charter before detailed solution development.
2 | Use Stage Gates proportionately. A gate is evidence that the project is ready to proceed.
3 | Maintain Programme & Actions as the working delivery plan.
4 | Use RAID to make risks, assumptions, issues and dependencies visible.
5 | Track committed, actual and forecast cost - not only invoices received.
6 | Use Supplier Comparison to separate technical/lifecycle suitability from price.
7 | Complete Design Review before design freeze/order where practicable.
8 | Do not enter installation without readiness controls.
9 | Define FAT/SAT/commissioning acceptance criteria before testing.
10 | Record changes formally where scope, design, food safety, H&S, cost or programme changes.
11 | Use Snag List; do not allow unresolved critical items to disappear into handover.
12 | Handover must transfer the asset into Operations/Engineering systems including PM, calibration, spares, drawings, software and training.
13 | Review benefits after implementation and record lessons learned.
Important | PED-01 is an independent engineering framework. It does not replace CDM 2015 duties, statutory risk assessments, HACCP, official BRCGS/SQF requirements, contracts or competent professional advice.

## References
Reference | Relevance to PED-01 | AFME note | Official URL
HSE - Construction (Design and Management) Regulations 2015 guidance | Client project-management arrangements, time/resources, dutyholder appointments and construction-phase controls. | Apply where project activities fall within CDM; PED-01 does not replace legal compliance. | https://www.hse.gov.uk/pubns/books/l153.htm
BRCGS Global Standard Food Safety Issue 9 | Framework for product safety, integrity, legality, quality and operational controls in food manufacturing. | Project/design/change decisions should consider current site certification requirements. AFME is not a BRCGS certification body. | https://www.brcgs.com/our-standards/food-safety
BRCGS Food Safety Help & Guidance / F926 | Current Issue 9 supporting documents and mandatory position statements effective 10 August 2026. | Check current official position statements during project/change reviews. | https://www.brcgs.com/our-standards/food-safety/help-and-guidance
SQF Edition 10 resources | Edition 10 places increased emphasis on change management and food-safety-system control. | Use current official SQF code/guidance where applicable; AFME templates are independent. | https://www.sqfi.com/the-sqf-code